## Introduction
COGR Resources:
NIH DMS Resource Page
NIH DMS Readiness Guide
Institutional Briefing Sheet
Guidance Matrix
Roles & Responsibilities Considerations
To Print Roles & Responsibilities Spreadsheet (Second Tab)
Will print in 3 pages
Choose to print double or single sided
Introduction: The development of Roles and Responsibilities is a critical process to support your institution's implementation. It may drive communication/training delivery, costing decisions, resource allocation, and ability to support the research effectively. Using the RACI ( Responsible, Accountable, Consulted, and Informed) methodology also ensures clarity of accountability while also ensuring that appropriate stakeholders are engaged.
Recommended Process to Develop an Effective R&R Implementation Document:
A) Discuss the COGR Institutional Briefing Sheet with senior leadership (Operations, Library, IT, Faculty, etc.). Review COGR Resource
Page, including the Guidance Matrix, Sheet, Considerations Document, R&R’s, etc.
B) Develop a Committee of Stakeholders and Process Owners; ensure it considers your organizational structure and culture. Likely
participants will include the library, research administration, IT, leadership, and faculty, among others.
C) As needed, develop supporting analysis - Estimate how many Data Management & Sharing Plans (DMSPs) will be submitted
annually based on available data to support volumes; inventory where your organization may already have some organizational
competencies in developing and implementing DMSPs. This analysis could include:
a. Awards >$500k by faculty and department
b. NSF volume
c. Submission cycles
d. Survey of expertise in DMP development expertise
e. Analysis of whether your faculty may have low or high-intensity DMS plan support requirements
f. Analysis of proposal and award overall volume and patterns
D) Review R&R document.
a. This document will likely need to be customized to address the structure and culture of your institution.
b. Evaluate rows (activities) for adequacy and completeness of detail based on your institution. In many cases, you may choose to delete some activities and add detail in may other areas.
c. Evaluate columns (roles) as these will be very different based on your structure, level of decentralization, and organizational hierarchy and associated lines of authority.
d. Are “Responsibilities” at the right level? Add or delete as needed for your institution.
e. Review Roles: is this how your organization is structured? Do you need to add, delete or change?
E) Consider developing FAQ’s specific to your institution and a resource page.
F) Develop a communication strategy - begin with raising awareness now and slowly start providing more detailed guidance up
to and through the effective date.
This document may be updated from time to time, and we encourage you to check COGR's Readiness Guide page (linked at the top of the next column under "COGR Resources") for the latest version.
If you have any questions about this document, please contact David Kennedy at dkennedy@cogr.edu and Krystal Toups at ktoups@cogr.edu .
V.1, Released November 8, 2022

## Roles and Responsibilities
Version 11/8/22
Roles and Responsibilities: Lifecycle Data Management & Sharing
Preamble: the Introduction tab provides details for considerations as an institution uses this document. It is important for an institution to customize this spreadsheet based on its specific organizational hierarchy, level of decentralization, differing areas of expertise, etc. Institutions will likely add and delete rows (activities/responsibilities) and columns (roles) specific to their implementation of this regulation.
# | Responsibility / Activity | [6 empty] | Role
| Lifecycle Public Data Access Activities | Lifecycle / Timing | NIH / Peer Review / Program Staff / OPERA | Legal / Regulatory / Etc. | Single POC to Triage Issues and Support | Library | Repository | VPR | PI | Tech Transfer | Postdoc / Grad Student | Dept. Grant Support Staff | Pre-award (Central Office) | Post-award (Central Office) | Central Compliance Oversight & Monitoring | Research Program Developm't | Human Research Support (as applicable) | Institutional Data Management Support | Proc. / Other | IT | Costing / Accounting | Training | Other
0 | Confirmation/Development of Community Standards: Research teams work with colleagues, internal and external to institution, to identify, develop, and apply community data and sharing standards in general and specific to their discipline. Develop and provide training on the DMS Policy & Process. Develop support process, such as a single Point-of-Contact and/or Triage Process to respond to urgent issues. | Infrastructure / Pre-Proposal | In Process
| Developing and working with discipline-specific data managers and support staff; engaging with research societies who have a critical role in developing standards | Infrastructure / Pre-Proposal
| Working with CORES (may have experience in interacting with large datasets) and institutional service providers to evaluate storage and data management options to support your institutions and scientific discipline | Infrastructure / Pre-Proposal and At Proposal
| Developing and provide training on the DMS Policy & Process for faculty, grants office, support teams, post-docs, research admins, etc. | Infrastructure / Pre-Proposal
| Identifying a single Point-of-Contact and Triage Process for required clarifications and issues that require escalation internally and to NIH; critical at deadline for submission, etc. | Infrastructure / Pre-Proposal
| Based on risk, burden management, and level of decentralization: evaluating effectiveness of internal control environment related to Data Lifecycle (policy, procedures, training, monitoring, technology leveraged). Throughout organization, from grad student/postdoc, faculty through departmental research administration to central offices, do you have the necessary controls and infrastructure in place to create the necessary support for the culture of data management? | Infrastructure / Life-cycle
1 | Planning, Design and Start up of projects
| Determining if your proposed research is subject to the DMS policy | At Proposal | IC will provide all necessary DMS requirements in NOA
| Reviewing Funding opportunity announcement for requirements and specific guidance related to the awarding IC | At Proposal
| Identifying appropriate methods/approaches and repositories for managing and sharing scientific data | At Proposal
| Reviewing institutional tools/guidance/resources related to your specific discipline | At Proposal | In Process
| Review COGR readiness guide (Policy Matrix, Considerations, Overview document) | At Proposal
| Evaluating institutional roles & responsibilities for critical steps in the DMS Plan support | At Proposal
| Identifying a data resource manager of knowledgeable individual that can assist with technical aspects of policy/guidance, as needed | At Proposal
| Preparing a data management plan (note that applications subject to both the DMS Policy and the GDS Policy will submit a single Plan) | At Proposal
| Reviewing IC-specific data sharing expectations that apply (e.g., scientific data to share, relevant standards, repository selection, timelines) and should be reflected in a Plan. See details in the NOA. | At Proposal
| Ensuring all Elements from Notice are addressed (Data Type, Related Tools, Software and/or Code, Standards, Data Preservation, Access, and Associated Timelines, Access, Distribution, Reuse Considerations, Oversight of Data Management and Sharing) | At Proposal
| Reviewing and addressing all data elements required from NIH notice and ICs guidance - Data Type | At Proposal
| Reviewing and addressing all data elements required from NIH notice and ICs guidance - Related Tools, Software and/or Code | At Proposal
| Reviewing and addressing all data elements required from NIH notice and ICs guidance - Standards | At Proposal
| Reviewing and addressing all data elements required from NIH notice and ICs guidance - Data Preservation, Access, and Associated Timelines | At Proposal
| Reviewing and addressing all data elements required from NIH notice and ICs guidance - Access, Distribution, or Reuse Considerations | At Proposal
| Reviewing and addressing all data elements required from NIH notice and ICs guidance - Oversight of Data Management and Sharing | At Proposal
| Adjusting DMSP as needed based on change in science | JIT
| Responding to peer reviewers comments on the proposed budget for data management and sharing (comments do not impact the overall score) | Peer Review
| NIH Program Staff review of Plans, review of updates, and compliance monitoring | Peer Review
| Non-competing renewals | Life
| DMSP included in Award T&C's | Award Start-Up
| DMSP adjusted as needed based on science and landscape changes (updated during the course of the award/support period to reflect any changes in the management and sharing of scientific data) | Life
| Evaluating security implications (see "Elements" section above) | At Proposal and Life
| Determining Repository/Storage solution | At Proposal
| Preparing IRB protocols and informed consent for data sharing | At Proposal
| Determining any intellectual property, licensing, and copyright considerations | At Proposal
| Developing any materials transfer and data use agreements | At Proposal
| DMP Compliance with DUA | At Proposal and Life
| Budget - determining cost: Including Reasonable costs allowed in budget requests (Curating data/developing supporting documentation, Preserving/sharing data through repositories, & Local data management considerations) | At Proposal
| Evaluating potential use of cost estimation tool Determine service needs Nbr units needed Translate into budget needs Office reviews https://sharing.nih.gov/data-management-and-sharing-policy/planning-and-budgeting-DMS/budgeting-for-data-management-sharing | At Proposal
| Publication Fees (often based on size and duration of data) | At Proposal
| Evaluating implications on existing resources, as required (e.g. post docs that will be required to manage data that may impact their ability to support project in other ways) | At Proposal
| Institutional approval/review of content, budget, etc. (e.g. to ensure that PI hasn’t committed data retention requirements for 10 years when 3 would be adequate) | At Proposal/JIT
| Who, what, where and how - Trigger points for escalated review. Areas to consider for a review: budget, data storage commitments, compliance with NOA and Terms & Conditions, compliance with DUA, security, IRB, etc. Issue: Institutional role for "approval" - may need multiple different offices. Support options: provide a set of questions to the GM to discuss with the PI? Compensating controls? | At Proposal/JIT
2 | Data Collection, Storage, and Management
| NOTE: differences related to activities below if using a repository (internal or external) | THIS MAY VARY SIGNIFICANTLY IF IT IS AN EXTERNAL REPOSITORY
Developing documentation of data (data dictionary, protocols)
Creating quality control mechanisms or procedures
Ensuring research staff have a mechanism to ensure active management and meeting any prior approval requirements for changes, as applicable
Coordinating changed DMS Plan with sponsor
Evaluating data analysis tools and processes to support sharing and reproducibility
Managing active data (storage, security, backup, lab notebooks)
Institutional monitoring and approvals; award is made to the institution - what are NIH's expectations in this space? Monitoring data management plans: review all required elements of the DMS Plan and evaluate for changes that may need coordination and/or coordination with Program staff
Adjusting DMSP as needed based on science and landscape changes (updated during the course of the award/support period to reflect any changes in the management and sharing of scientific data, e.g., new scientific direction, new repository option, timeline revision)
Data Ingest (prepare for data analysis, extract-transform-load)
Evaluating collaboration and sharing data needs with team and any subrecipients; consider DUA, IRB, Terms & Conditions and associated security implications
3 | Making Data Broadly Available
Making decisions about what data to share or host
Providing or hosting repositories for making data available
Preparing data for sharing, e.g., de-identification, curation
Creating documentation for sharing (structured metadata) = Repository may have a form/format that documents this
Selecting or applying licenses to data
Migrating formats of data to be open or more accessible
DMP Compliance with DUA
Determining who can have access to the data: institution and/or study team may make this determination
Creating persistent identifiers
4 | Data Retention, Including Preservation, Archive, and Long-Term Access
Post award monitoring (dept, central, IA)
Migrating files to new formats or systems as needed
Monitoring integrity of preserved data
Making decisions about de-accessioning and removal of research data
Data Security (PHI, HIPAA, Export Controls, FISMA, student data and IP)
Consider de-identification, if necessary
5 | Project Closeout and Compliance
Ensuring funding agency requirements for data sharing have been met
Compliance support around research project reports
NIH Institute/Center confirmation of data plan execution and quality
| Confirmation of compliance with DMSP Plan - will continue well beyond the end of the award end-date | Post-Closeout / During Life of Data Retention Requirement
Consider using the Responsibility assignment matrix: Identify who is Responsible, Accountable, Consulted, and Informed for each activity.
Responsibility assignment matrix - Wikipedia